OHI Hawaiʻi Communication Strategy

The OHI will be shared via:

- Website ohi-science.org/mhi

  - Need to polish the website design, figure resolutoin, consistent font size and type

- Dashboard dashboard.hawaii.gov

  - need score card like template to display results

- Large Rollout Event at UH presidents hill with local legislatures, govenor, former presidents

- 1 pager on results with main messages (to be approved by stakeholders and partnering agencies)

- Blog/press release

Timeline:

February – review index results and messaging with stakeholders and partners

March – develop communication materials, website, and report

Late March/Early April – review communication materials with partners for approval

Roll Out April 20th

Press release/blog